## Sheet1
Three Hand Poker Game - Project Schedule
Team Name: UTC Poker Club
| Project Manager: |  |  | James Hare
| Project Start Date: |  |  | 2017-09-26 | time axis 2017-09-25 to 2017-11-20
| Display Week: |  |  | 1 |  |  |  |  | 2017-09-25: Week 1; 2017-10-02: Week 2; 2017-10-09: Week 3; 2017-10-16: Week 4; 2017-10-23: Week 5; 2017-10-30: Week 6; 2017-11-06: Week 7; 2017-11-13: Week 8
[9 empty] | 2017-09-25 | [6 empty] | 2017-10-02 | [6 empty] | 2017-10-09 | [6 empty] | 2017-10-16 | [6 empty] | 2017-10-23 | [6 empty] | 2017-10-30 | [6 empty] | 2017-11-06 | [6 empty] | 2017-11-13
WBS | Task | Lead | Prede cessor | Start | End | Cal. Days | % Done | Work Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
0 | Kick Off
0.1 | Deliver group information to user | James Hare |  | 2017-09-26 | 2017-10-03 | 8 | 100% | 6
0.2 | Compile group member information | Daniel Velasquez |  | 2017-09-26 | 2017-09-26 | 1 | 100% | 1
0.3 | Organize card game rankings | Richard Kimsey |  | 2017-09-27 | 2017-09-28 | 2 | 100% | 2
0.4 | Establish team name and meeting times | Loro Dumo |  | 2017-09-26 | 2017-09-26 | 1 | 100% | 1
0.5 | Coordinate text activities and communications | Javier Martinez |  | 2017-09-27 | 2017-10-01 | 5 | 100% | 3
1 | Sprint 1 - Deadline Oct 12
1.1 | Research Gameplay rules and implementations for three hand poker | James Hare |  | 2017-10-03 | 2017-10-11 | 9 | 100% | 7
1.2 | Research component architecture including languages and IDEs | Daniel Velasquez |  | 2017-10-03 | 2017-10-11 | 9 | 100% | 8
1.3 | Complete Project Documentation Section 2 - Management | Loro Dumo |  | 2017-10-03 | 2017-10-11 | 9 | 100% | 7
1.4 | Begin Project Documentation Section 1 - Introduction | Richard Kimsey |  | 2017-10-02 | 2017-10-11 | 10 | 100% | 8
1.5 | Begin Project Documentation Section 1.1 - Purpose | Richard Kimsey |  | 2017-10-04 | 2017-10-11 | 8 | 100% | 6
1.6 | Begin Project Documentation Section 2.2 - Software Validation | Javier Martinez |  | 2017-10-02 | 2017-10-11 | 10 | 100% | 8
1.7 | Determine the scope and fill out Section 1.2 - Scope | James Hare |  | 2017-10-03 | 2017-10-11 | 9 | 100% | 7
1.8 | Complete Project Documentation Section 2.3 - Configuration Plan | Daniel Velasquez |  | 2017-10-03 | 2017-10-11 | 9 | 100% | 7
2 | Sprint 2
2.1 | Begin Project Documentation Section 1.1 - Purpose | James Hare |  | 2017-10-10 | 2017-10-24 | 14 | 100% | 11
2.2 | Search for Reusable Card Game Code | Daniel Velasquez |  | 2017-10-11 | 2017-10-24 | 13 | 100% | 10
2.3 | Begin Project Documentation Section 5 - Implementation Strategy | Javier Martinez |  | 2017-10-12 | 2017-10-24 | 12 | 100% | 9
2.4 | Install and Configure Visual Studio on computer | Loro Dumo |  | 2017-10-13 | 2017-10-24 | 11 | 100% | 8
2.5 | Research graphical user interface integration with backend C# code | Richard Kimsey |  | 2017-10-14 | 2017-10-24 | 10 | 100% | 7
2.6 | Play Three Hand Poker | Team Activity |  | 2017-10-14 | 2017-10-24 | 10 | 100% | 7
2.7 | [Insert Rows above this one, then Hide or Delete this row]
3 | Sprint 3
3.1 | [Task] |  |  | 2017-09-26 | 2017-09-26 | 1 | 0% | 1
3.2 | [Task] |  |  | 2017-09-27 | 2017-09-27 | 1 | 0% | 1
3.3 | [Task] |  |  | 2017-09-28 | 2017-09-28 | 1 | 0% | 1
3.4 | [Task] |  |  | 2017-09-29 | 2017-09-29 | 1 | 0% | 1
3.5 | [Insert Rows above this one, then Hide or Delete this row]
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
CATEGORY ROWS and WBS NUMBERING
1 | [ Task Category (label only) ]
1.1 | [ Level 2 Task ]
1.1.1 | . [ Level 3 Task ]
1.1.1.1 | . . [ Level 4 Task ]
Examples of ways to define tasks
1 | [ Task Category (summary) ] |  |  | 2015-04-01 | 2015-04-17 | 17 |  | 13
2 | Milestone |  |  | 2015-04-01 | 2015-04-01 | 1 |  | 1
2.1 | [ Start Date and Calendar Days ] |  |  | 2015-04-01 | 2015-04-03 | 3 |  | 3
2.2 | [ Start the next day after another Task ] |  |  | 2015-04-04 | 2015-04-10 | 7 |  | 5
2.3 | [ Start next work day after another Task] |  |  | 2015-04-13 | 2015-04-17 | 5 |  | 5
3.6 | Complete Project Documentation Section 1.3 - Terminology | James Hare |  | 2017-10-14 | 2017-10-24 | 10 | 100% | 7
4 | Sprint 3
4.1 | Complete Program Logic for Winning Cards | Daniel Velasquez |  | 2017-10-25 | 2017-11-08 | 14 | 100% | 11 | bar: 2017-10-23 W to 2017-11-06 W
4.2 | Create Game Selection Interface | Richard Kimsey |  | 2017-10-25 | 2017-11-08 | 14 | 100% | 11 | bar: 2017-10-23 W to 2017-11-06 W
4.3 | Create UML Diagrams | Loro Dumo |  | 2017-10-25 | 2017-11-08 | 13 | 100% | 9 | bar: 2017-10-23 T to 2017-11-06 W
4.4 | Create Class Diagrams | Daniel Velasquez |  | 2017-10-25 | 2017-11-08 | 13 | 100% | 9 | bar: 2017-10-23 T to 2017-11-06 W
4.5 | Create test classes for system | Javier Martinez |  | 2017-10-25 | 2017-11-08 | 12 | 100% | 9 | bar: 2017-10-23 T to 2017-11-06 W
4.6 | Work towards completing all remaining sections of Project Document | James Hare, Loro Dumo |  | 2017-10-25 | 2017-11-08 | 12 | 100% | 9 | bar: 2017-10-23 F to 2017-11-06 W
5 | Sprint 4
5.1 | Implement GUI | Richard Kimsey |  | 2017-11-08 | 2017-11-15 | 8 | 100% | 6 | bar: 2017-11-06 W to 2017-11-13 T
5.2 | Export solution as a Windows console application | Daniel Velasquez |  | 2017-11-08 | 2017-11-15 | 8 | 100% | 6 | bar: 2017-11-06 W to 2017-11-13 T
5.3 | Complete all remaining sections of section 4 of Project Document | James Hare |  | 2017-11-08 | 2017-11-20 | 13 | 100% | 9 | bar: 2017-11-06 W to 2017-11-13 S
5.4 | Complete all remaining parts of section 3 of Project Document | Loro Dumo |  | 2017-11-08 | 2017-11-20 | 13 | 100% | 9 | bar: 2017-11-06 W to 2017-11-13 S
5.5 | Obtain Windows console application from 5.3 and work towards completing more tests | Javier Martinez |  | 2017-11-15 | 2017-11-20 | 6 | 100% | 4 | bar: 2017-11-13 T to 2017-11-13 S
5.6 | Complete all remaining parts of Project Document | Group activity |  | 2017-11-15 | 2017-11-20 | 6 | 100% | 4 | bar: 2017-11-13 T to 2017-11-13 S